## Sheet1
Hospital Name | Project ID | Project Type | Project SPOC | Project Start Date | Project Completion Date | Delay Category | Primary Delay Drivers | Specific Event / Description | Impacted Task | Root Cause | Responsibility | Delay_Start Date | End Date | Total Days Delayed | Delay Severity | Mitigation Action Taken | Status | "Early Warning System" (EWS) | Direct Cost | Opportunity Cost | Target Revised Completion Date | Before & after pic | Project document _Attachment
|  | New projects (Green field / Brown Field), Renovation |  | DD/MM/YY | DD/MM/YY |  | (Explanation of 'Category' buckets | Describe specific task delayed (e.g., "Installation of MRI Shielding") | Impact on the Critical Path | Planning gap, Coordination failure, Vendor underperformance, Design change, Approval bottleneck, Resource constraint | Who is responsible (Contractor, Architect, Hospital Admin or External Vendor) | The start date of the delay DD/MM/YY | the date it will be resolved DD/MM/YY | in Days | Minor (1-7 days) Moderate (8-30 days) Critical (>30 days) Showstopper (impacts licensing/ opening) |  |  | If a sub-task (like medical gas piping) hits 80% of its allotted time but is only 50% complete, the framework should auto-flag it as a "Potential Delay" | Overruns in labor and materials | Lost revenue from delayed surgeries, patient admissions
| Hosp name_Renovation / Construction_001 |  |  |  |  | Regulatory & Permitting | Long wait times for environmental, fire safety, PCPNDT, AERB approvals | Pending Fire inspection for Annex building | Final NOC | Planning Gap
| Hosp name_Renovation / Construction_002 |  |  |  |  | Design & Scope | Mid-construction changes. Late-stage requests from clinicians to change room layouts or equipment | CSSD Uni-directional flow | ICU Headwall Installation | Design Change | Dr X | 2026-02-03 | 2026-02-20 | 17 |  | Change Order #42 outlets issued
| Hosp name_Renovation / Construction_003 |  |  |  |  | Supply Chain | Long-lead items (MRI machines, custom AHUs etc), delayed by the vendor, halting the final inspection | MRI Shielding materials stuck in transit | Imaging Suite Completion | Approval Bottleneck | Procurement Head
| Hosp name_Renovation / Construction_004 |  |  |  |  | Specialized Labor | Shortage of certified / specific manpower lead-shielding installers |  |  |  | Project In-charge
| Hosp name_Renovation / Construction_005 |  |  |  |  | Operational Readiness | Delays in hiring/training staff, IT systems not being ready | IT hardware delay | EMR go-live |  | IT Head
| Hosp name_Renovation / Construction_007 |  |  |  |  | Infection Control Compliance | Dust barriers or air pressure |  |  |  | Project In-charge
[6 empty] | Site Condition Surprises | Discovery of existing structural or any plumbing issues that were not in the original plan |  |  |  | Project In-charge
[6 empty] | Logistical Challenges | Inability of contractors to move materials due to active patient traffic, leading to night-work delays |  |  |  | Project In-charge

## Construction
Hospital Name | Project ID | Project Type | Area / Facility | Project SPOC | Project Start Date | Project Completion Date | Delay Category | Primary Delay Drivers | Specific Event / Description | Impacted Task | Root Cause | Responsibility | Delay_Start Date | End Date | Total Days Delayed | Delay Severity | Before & after pic | Mitigation Action Taken | Status | "Early Warning System" (EWS) | Direct Cost | Opportunity Cost | Target Revised Completion Date | Project document _Attachment
|  | New projects (Green field / Brown Field), Renovation | Individual Depts or Facility |  | DD/MM/YY | DD/MM/YY | MEP / Procurement & Supply Chain / Design & Scope / Medical Equipment Installations / Regulatory Approvals / Specialized Labor / Logistical Challenges / Site Condition Surprises / Operational Readiness / Infection Control Compliance | (Explanation of 'Category' buckets | Describe specific task delayed (e.g., "Installation of MRI Shielding") | Impact on the Critical Path | Planning gap, Coordination failure, Vendor underperformance, Design change, Approval bottleneck, Resource constraint | Who is responsible (Contractor, Architect, Hospital Admin or External Vendor) | The start date of the delay DD/MM/YY | the date it will be resolved DD/MM/YY | in Days | Minor (1-7 days) Moderate (8-30 days) Critical (>30 days) Showstopper (impacts licensing/ opening) |  |  |  | If a sub-task (like medical gas piping) hits 80% of its allotted time but is only 50% complete, the framework should auto-flag it as a "Potential Delay" | Overruns in labor and materials | Lost revenue from delayed surgeries, patient admissions
Apollo Hospitals, Gurugram | AH-Gurugram - CONST-01 | Green Field | Emergency | Mr.Biomedical | 2026-06-15 | 2026-06-21 | Regulatory Approvals | Long wait times for environmental, fire safety, PCPNDT, AERB approvals | Pending Fire inspection for Annex building | Final NOC | Planning Gap |  |  |  |  | Showstopper (Impacts licensing/opening)
Apollo Hospitals, Gurugram | AH-Gurugram - CONST-02 | Green Field | MRI Room | Mr.Operations | 2026-06-25 | 2026-06-30 | Design & Scope | Mid-construction changes. Late-stage requests from clinicians to change room layouts or equipment | CSSD Uni-directional flow | ICU Headwall Installation | Design Change | Dr X | 2026-02-03 | 2026-02-20 | 17 | Moderate (8-30 days) |  | Change Order #42 outlets issued
| Hosp name_Renovation / Construction_003 | [5 empty] | Supply Chain | Long-lead items (MRI machines, custom AHUs etc), delayed by the vendor, halting the final inspection | MRI Shielding materials stuck in transit | Imaging Suite Completion | Approval Bottleneck | Procurement Head
| Hosp name_Renovation / Construction_004 | [5 empty] | Specialized Labor | Shortage of certified / specific manpower lead-shielding installers |  |  |  | Project In-charge
| Hosp name_Renovation / Construction_005 | [5 empty] | Operational Readiness | Delays in hiring/training staff, IT systems not being ready | IT hardware delay | EMR go-live |  | IT Head
| Hosp name_Renovation / Construction_007 | [5 empty] | Infection Control Compliance | Dust barriers or air pressure |  |  |  | Project In-charge
[7 empty] | Site Condition Surprises | Discovery of existing structural or any plumbing issues that were not in the original plan |  |  |  | Project In-charge
[7 empty] | Logistical Challenges | Inability of contractors to move materials due to active patient traffic, leading to night-work delays |  |  |  | Project In-charge

## Renovation Projects
Project ID | Project Scope | Location | Project Name | Zone/Department Impacted | Renovation Type | Task Category | Task Description | Priority | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Delay Days | Shutdown Required | Patient/Service Disruption Score | Temporary Relocation Needed | Infection Control Clearance | Dependency Task | Risk Score | Budgeted Cost | Actual Cost | Cost Overrun % | Vendor/Contractor | Procurement Status | Material Delay Days | Approval Status | Approval Pending Days | Change Orders | Escalation Status | Daily Delay Reason | Final Handover Date | Project Status | Remarks
REN-001 |  |  | ICU Renovation |  |  |  |  | High | 2026-06-01 | 2026-06-15 | 2026-06-02 | 2026-06-18 | 3 | Yes | 9 | Yes | Approved | Design Approval | 8 | 500000 | 575000 | 0.15 | ABC Infra | Ordered | 5 | Pending | 7 | 2 | Escalated | Material shortage | 2026-06-20 | In Progress | Critical care area
REN-002 |  |  | OPD Upgrade |  |  |  |  | Medium | 2026-07-01 | 2026-07-10 |  |  |  | No | 4 | No | Approved | Vendor Finalization | 5 | 150000 | 0 |  | XYZ Electrical | Pending | 0 | Approved | 0 | 0 | None |  |  | Planned | Minimal disruption